## Sheet1
Bovey Tracey Town Council
Capital Programme - Draft plan (2021/22-2026/27)
[10 empty] | Strategic Fit | Resident/Parish Need | Feasibility | Future economic growth | Climate and environment | Resident social wellbeing | Ongoing, Maintenance Liabilities | Affordability (Capital) | Affordability (Revenue) | Overall Score
Project | Proposed funding source | Committee Owner | 2021/22 | 2022/23 | 2023/24 | 2024/25 | 2025/26 | 2026/27 | Comments | Yes 3, No 0 | Essential 3, Important 2, Important but could be deferred 1, Not required 0 | High 3, Medium 2, Low 1 | High 3, Medium 2, Low 1 | High 3, Medium 2, Low 1 | Yes 3, No 0 | High 1, Medium 2, Low 3 | Low cost 3, Medium cost 2, High cost 1 | Low cost 3, Medium cost 2, High cost 1
Heathfield
Prince Rupert Way Play Area Upgrade/Expansion (owned by TDC) | TDC funding | RP&P | 2022/23: 25000 | TDC Play Officer has scheduled the refurbishment into her list of schemes. | 3 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 2 | 19
Heathfield Youth Cabins - Replacement of existing cabins | BT capital/other grants | RP&P | 2022/23: 40000 | Current cabins are coming to the end of their natural life and are failing in places. | 3 | 2 | 2 | 1 | 1 | 3 | 2 | 2 | 2 | 18
Bovey Tracey
Create 10 additional allotments - Brimley Field | BT capital | RP&P | 2022/23: 5000 | Funding from Brimley Field Disposal. Legally required to deliver as part of Development Framework for site | 3 | 2 | 3 | 1 | 3 | 3 | 2 | 3 | 3 | 23
Bike storage hubs | Lottery grant/BT capital | RP&P | 2023/24: 7000 | Resistence from TDC to allocate/dispose of bays within car parks. | 3 | 1 | 2 | 1 | 3 | 3 | 3 | 2 | 3 | 21
Car park Resurfacing at the Recreation Ground (Pothole fix) | S106 or BT capital | RP&P | 2022/23: 20000 | Current car park condition is poor. Legal obligation to provide safe and hazzard free parking. | 3 | 3 | 3 | 1 | 1 | 3 | 2 | 2 | 2 | 20
Refurbishment of existing Basketball Area in Mill Marsh Park | BT Capital/S106/CiL | RP&P | 2023/24: 20000 | Combine Basketball Area Refurb with tender for refurbishing Play Area in Mill Marsh Park | 3 | 2 | 2 | 1 | 1 | 3 | 3 | 2 | 3 | 20
Way finder lighting along Accomodation Lane to provide a safe connection between B Tracey & Heathfield | BT/Grant | RP&P | 2023/24: 3791 | Quote obtained, however freedback from the Planning Authority was that this is a sensitive area for additional lighting. | 3 | 2 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 20
Football Pavillion Redevelopment/ Refurbishment Project at the Recreation Ground | BT capital | RP&P | 2023/24: 50000 | Architects to produce floorplan and visuals ahead of Expressions of Interest being sought via a commercial agent, before proceeding with work. | 3 | 2 | 2 | 3 | 2 | 3 | 1 | 1 | 2 | 19
EV Charging Point - St Johns Lane Car Park (BTTC Owned land) | DCC Grant Funding | Planning & Env. | 2023/24: 6000 | Awaiting feedback on draft lease from Gamma Energy. | 3 | 1 | 2 | 1 | 3 | 3 | 2 | 2 | 2 | 19
Solar Photovoltaic Panels - Riverside Community Centre | Lottery grant | RP&P | 2021/22: 28000 | System will be live by December 2022 | 3 | 2 | 3 | 2 | 3 | 0 | 2 | 1 | 2 | 18
External storage unit for Centre Hirers - Riverside Community Centre | Lotttery grant | RP&P | 2023/24: 5000 | Grant committed by the National Lottery. Storage offering for potential hall hirers. | 3 | 1 | 2 | 1 | 1 | 0 | 3 | 3 | 3 | 17
Installation of Waylighters - Mill Marsh Park | BT Capital | RP&P | 2024/25: 10000 | Trial underway - to be progrssed by FoMMP. | 3 | 1 | 2 | 1 | 1 | 3 | 1 | 2 | 3 | 17
Replacement Grounds Maintenance Vehicle | BT capital | RP&P | 2023/24: 30000 | Consider electric vehicle if specification is affordable and meets requirements | 3 | 2 | 2 | 1 | 1 | 3 | 2 | 1 | 2 | 17
Play area Refurbishment/ Redevelopment, including replacement fencing etc (Mill Marsh Park) | TDC - S106 or other grants | RP&P | 2023/24: 125000 | 2 site visits held and approx quotes provided. Full Tender Pack to be drafted. | 3 | 2 | 2 | 1 | 1 | 3 | 1 | 1 | 2 | 16
Enhancements to Riverside Community Centre to better accommodate hirers | BT Capital | RP&P | 2024/25: 50000 | Awaiting feedback from Architects around possible options to enhance offering to hall hirers. | 3 | 1 | 2 | 2 | 1 | 0 | 2 | 1 | 3 | 15
Co-operative Carpark/Station Road Safer Crossing Scheme | TDC Highways | Planning & Env. | 2023/24: 30000 | Awaiting feedback from DCC as to the allocation/availability of TDC S106 contributions | 3 | 1 | 1 | 1 | 1 | 3 | 1 | 1 | 1 | 13
Annual potential total capital requirement |  |  | 28000 | 90000 | 276791 | 60000 | 0 | 0
KEY
Projects over £10,000 requiring a PID
Projects to be potentially externally funded (Grants/S106 etc)
Project value below £2,500 so Town Clerk/Chair of Finance to Consider