Bovey Parish Neighbourhood Plan

Minutes of the 34th Steering Group ONLINE Meeting

17th November 2020 at 7.00 pm

Attending:

Mark Bailey (MB)

Cllr Robert Bradshaw (RB) - Chair

Cllr Sheila Brooke (SB) - ex officio

Marion Edwards (MEd)

Martyn Iles (MI)

Alan Taylor (AT)

Lisa Robillard Webb (LRW) – Minute-taker

- Welcome, Introductions & Apologies: - None given.

- Declaration of Interests: - None declared.

- Climate Emergency: - Statement noted.

- Minutes: -

4.1 - Approval of minutes: 20th October 2020 minutes agreed by all.

4.2 Review of Actions:

Summary of Actions:

- Completed - MB to speak with Frances Billinge and Viv Styles about the Historic Environment Officer’s feedback.  To seek a view/solution from ML and circulate the outcome to the SG and MW

- Completed - MEd to circulate her suggested changes to column headings on the Consultation Table Layout to the SG

- Completed - MI to help SB with Housing feedback - meet via Zoom

- Completed - SB to check with DF about what support she needs in the Land & Environment feedback

- Completed - RB& MEd to meet and discuss Business & Employment and Community Services & Facilities feedback

- Completed (Heads of Terms being negotiated with DCC, then statement go to BTTC at next full council meeting) - SB/RB to check with MW on forthcoming BTTC meetings for suitable times to discuss BTPS and Le Molay Littry site

- Completed - RB to look at the General Comments respondents’ document

- Completed (Incorporated into the Consultation Statement, no changes made to Plan) - MI to look at the Community Organisations’ feedback

- Completed - LRW to go through the remaining large, generic feedback documents (eg Natural England and DCAF) to see if any specific areas need to be extracted into the feedback documents

- Completed - LRW to assist DF by highlighting the key areas of some relevant documents for Land & Environment

- Completed - Work-stream Leads to:

  - make suggested word changes.  Any policy changes should be collated in a table by the Workstream Leads and circulated for sign-off via e mail to the SG.

- Matters arising not on the agenda:

5.1: To receive matters arising not covered on the agenda: None given.

- Notified Items:

6.1:  Discuss and agree changes to the plan review process (RB):

- Draft plan to LB Planning for review

- LB Planning comments returned

- Changes made to the draft

- Revised draft plan sent to the proof-readers

- Final version to Ben at Promo Lounge

- Submit to TDC no later than the end of the first week in December.

6.2: Review the timeline in view of 6.1 above (RB/MI):

If TDC return Plan on time, it can go to BTTC full council meeting on 25th January 2021 (MI).  TDC have a six week turnaround period and they have seen the Plan three times already. RB will ask MW to put this on the agenda.  MI will change the final programme to the third week in September 2021.

* Discussion continued under 7, but minuted here.  Programme allows time for BTTC Councillors to comment on the Plan (MI) – circulate to them after LB Planning’s forthcoming review and at the same time of TDC review, so that there is time for comment and amendment prior to the full BTTC council meeting on 25th January 2021.  Any delay could be handled by an EGM to ensure sign-off of the Plan (SB).

MI noted that the SG should consider the time taken to appoint an Examiner so that one is in place for when the Plan returns from TDC.  TDC often informally indicate that the Plan can go forward to examination.

6.3: Review process of creating submission version and submitting plan (RB):

TDC have withdrawn from the GESP so the paragraph in the Plan will be deleted; for TDC, the Local Plan will be paramount (MEd).

The Statutory Consultees’ comments on the Plan will be made into Appendix 31 and available through a link (MEd).

RB will look at the Basic Conditions Statement and will send to LB Planning. MI noted that the Examiner will look at this document in detail.

MEd is working on the current version of the Consultation Statement, will need to insert Table 3, Section 6 and Front Cover.  General Comments from respondents will be inserted into the Consultation Statement. Community Questionnaire Report is not in the Appendices and it is a large document (MW has a copy).  TDC would probably need electronic copies instead of paper ones (RB), however the proof-readers will need hard copies (SB).  MEd will liaise with MW to label up the documents so that they are easy to find.

6.4:  Review and agree summary of documents needed for the submission (MEd):

Partly discussed above in 6.3.

- AOB:

7.1 Items for the next agenda:

Discussion held on the programme and the impact of consultation with BTTC Councillors – minuted under 6.2*.

Thanks to LRW and MEd for their hard work on the documents so far.

12) Date of next online meeting:

Next NPSG Meeting on Tuesday 8th December 2020 at 7.00pm.

Summary of Actions:

- RB to ask MW to put the NP on the agenda for the full BTTC council meeting on 25 January 2021

- MI to change the final programme to the third week in September 2021

- MEd to delete paragraph in the Plan on the GESP

- MEd to turn the Statutory Consultees’ comments into Appendix 31 and request a link from MW

- RB to look at the Basic Conditions Statement and send to LB Planning

- MEd to insert Table 3, Section 6, General Comments table and front cover into the Consultation Statement

- MW to produce hard copies of draft documents for the proof-readers

- MEd to liaise with MW to label up the documents so that they are easy to find.