Bovey Parish Neighbourhood Plan

Minutes of the 29th Steering Group ONLINE Meeting

2nd July 2020 at 7.00 pm

Attending:

Mark Bailey (MB)

Cllr Robert Bradshaw (RB) - Chair

Cllr Sheila Brooke (SB) - ex officio

Marion Edwards (MEd)

Martyn Iles (MI)

Alan Taylor (AT)

Lisa Robillard Webb (LRW) – Minute-taker

- Welcome, Introductions & Apologies: - Apologies: Mark Wells (MW)

- Declaration of Interests: - None declared.

- Climate Emergency: - Statement noted.

- Minutes: -

4.1 - Approval of minutes: 4th June 2020 minutes agreed by all.  RB gave thanks to SB for chairing the NPSG meeting 4th June 2020.

4.2 Review of Actions:

- Completed, SB checked after the meeting and letter was sent to JA on 5 June 2020: SB will draft a thank you for Julie Arnold and share the current, draft Housing document

- Completed.  2 meetings held – 9th and 18th June.  RB read out the minutes, attendants agreed to them: EK, SB, MI (and someone from the Comms Group) will have a Zoom meeting early next week to discuss the right approach for public consultation in line with the legislation

    - MW will help with the practicalities

    - MI will provide a list of regulations

- Completed, AT redrafted, circulated and now incorporated into master plan: MEd will to draft a version of the Acknowledgements and circulate to the group with one week for comment

- Completed and fee paid: MW will liaise with MB on the likely expenditure of the consultant’s fees and request that it is put aside in one protected pot

- Completed: MW to let LB Planning know that they have been awarded the work.  But ask for the best possible price and emphasise the deadline of 22nd June so that the document can be circulated to councillors

    - MI will adjust programme accordingly

- Completed, finalised paper written: EK will read draft Business & Employment and make some small changes to circulate by Tuesday 9 June to all members

- Completed: MW to send draft Business & Employment onto consultant once EK and members have commented on the latest draft

- Completed, draft to be discussed in the meeting and changes subsequently made: MW will draft a short press release with a synopsis and timescales of the NP and add to website

- Waiting for appropriate time (ie start of the consultation).  MEd clarified that the design of the last poster can be used again: MI could put up some posters at key points – BTTC, BTPS, Mill Marsh Park etc to update public on progress

- Completed, response sent on Monday 15th June with full BTTC minutes: EK and MW coordinate a collective BTTC response on the draft TDC Local Plan by Friday 12 June by lunchtime

- Completed: MEd to make changes agreed to the Pre Submission as outlined in AOB

- Completed: MEd to liaise with Jason Cole on artwork

- Completed: All:

    - Read and comment on MEd’s draft Acknowledgements by the one week deadline

    - Read draft Business & Employment from EK and offer any comments by the deadline, otherwise agreement implied

    - Read draft TDC Local Plan and send comments to MW by 11 June evening.

- Matters arising not on the agenda:

5.1: To receive matters arising not covered on the agenda: None given.

- Chair and Vice Chair Reports

6.1: Chair Report:  None given.

6.2: Vice Chair Report: None given.

- Secretary and Treasurer Reports:

7.1: Secretary Report:  None given.

7.2: Treasurer Report (MB):

Income to date:         £13,278.00

Expenditure to date: £10,239.17

Current balance:        £  3,038.83 [split between £294.48 restricted (9.7%) and £2,744.35 unrestricted (90.3%) funds]

The NDP Basic Grant was increased by £1,000 to £10,000 in May so the amount still available from Groundwork UK is now £2,870.

- Notified Items:

8.1:  Plan Observations/Feedback from LB Planning (LBP), Michelle Luscombe (ML) & Cllr Allen (RB)

Initial feedback received from ML and LBP.  After this meeting’s discussion, Working Group Leads to make the appropriate changes to their section of the Plan.  Once all the changes have been made, the Plan can be re-submitted to ML to undertake the HRA and SEA.  Following the further feedback and relevant changes made, the consultation period can commence.  After the consultation and the resulting feedback updated (where appropriate) into the Plan, submission can take place.

Deadline of 12th July 2020 for revisions (DNP may take longer than four weeks to do HRA so the NPSG will communicate the preferred start date for the consultation period to them).

Housing:  SB (liaising with MI) on Housing section.  SB will send MEd the re-drafted document

Traffic: MI sent latest draft to the Traffic group.  AT indicated his agreement but no word yet from UA. AT noted Cllr Allen’s feedback and it had been incorporated into the draft. MI will send the re-drafted document to MEd.  MI noted that the Traffic Section needed to be sent to DCC asap for their approval.  MI will do this to get the process underway; MW has the relevant contact name

Business & Employment: RB will lead on this group’s work

Environment: RB will liaise with Debbie Fletcher (DF) about timescales

Community Facilities:  As the only group member, MEd asked for another SG member to review the section.  MI offered to help.

AT offered his help on Heathfield if SG members needed any assistance.

SB confirmed that all BTTC councillors had seen the draft Plan on Monday 29th June 2020.  SB/RB will give any relevant feedback.  There will be no need for councillors to review the Plan again as it has been given the ‘go-ahead’.

8.2 Pre-Submission Consultation Process (RB):

MI has circulated the revised programme with the new proposed dates; for the seven week consultation period, if it starts on 10th August it will end on 27th September 2020. RB noted that the Chair’s message and draft press release should be changed from six to seven weeks.  MI noted that these dates may need to change if the HRA or SEA is running late.

Discussion on MW’s draft press release took place but is minuted under 10.2.

MW will circulate the Briefing Note on Referendums (for NDPs), RB found it useful guidance. (Subsequently circulated on 6 July 2020.)

8.3 Welcome Intro/Chair’s Statement (RB):

MEd and MI compiled the first draft.  RB sent his comments back to MEd.  Draft circulated to SG members, comments to be sent to MEd.  Dates for a seven week consultation period need changing.

Discussion held on the list of statutory consultees (RB read them out). MI asked if these consultees need to see all documentation (for example, appendices etc).  Group agreed to contact all consultees via e mail with a specific Dropbox link to all the relevant supplementary documentation.  ML asked if the NPSG would review the Plan in light of her comments.  RB confirmed that they would.  SB wanted to check with ML that the Dropbox link was acceptable.

- Work group reports:   None except:

9.3 – Community Facilities: MEd checked with the group that the projects associated with the deleted section on the searchable amenities and facilities database can now also be deleted.  RB agreed as MW already holds such a list.

- Communications:

10.1 – Correspondence & Information: Not discussed

10.2 – Public Relations & Press Releases:

Thanks were given to MW for writing the draft. Consistency of language was important.  Changes to be made before release include:

- 3rd paragraph, 1st sentence change to ‘Parish Bovey including Bovey Tracey, Heathfield and surrounding area’

- Change ‘Bovey’ where applicable to ‘Parish’

- 1st paragraph, 1st Line ‘Bovey Tracey Town Councillors and community members worked together under the auspices of Bovey Tracey Town Council’

- Add in phone number and e mail address for contact details

- Confirmed dates

- ‘Hard copy available on request’

- 4th paragraph take out wording ‘Local Plan’ to avoid confusion.  Replace with wording along the lines of ‘In accordance with….’ and part of statutory development plan for the Parish’.

RB will give MW the changes.  The redraft will be circulated to SG for comment by a deadline.  MI confirmed that if the proposed consultation dates are kept, the Plan is on track for w/c 12 July 2021.

Leaflet:

MI wrote a summary for the Quality Update.  Royal Mail option very expensive and would deliver to some houses outside of the Parish and miss some houses within the Parish.  MW is looking at GPS tracking system for deliverers to ensure comprehensive coverage as proof for the Examiners.  RB stated that normally the Quality Update is delivered to 3,500 households which is 80% coverage.  Perhaps volunteers could do the remaining households (approximately 500 houses in outlying areas).  Phone number could be added to the Update (by MEd) and to the posters (MI).  A cost-effective mobile phone will be bought by RB/MW. An answer-phone service will be required.

- AOB:

11.1 Climate Impact:  Not discussed.

11.2 Brief items and/or to the next agenda:

Appendices and Front Cover: Discussion held on the compilation of appendices. Larger reference documents can be put in the main document but often they are put in the Appendices (MI).  MEd will ask Cllr Jason Cole (JC) to quote for this.  Draft cover design from JC is professional and clean, he kindly did this design for free.  The group would like to see an alternative design.  SB will check whether a number of quotes should be asked for as JC is a BTTC Councillor.

MEd suggested changing the Project List to the end of the Plan.  She also suggested that in Point 10 ‘Review Section’, the words ‘We will monitor and review…’ are quite vague.  She suggested a ‘biennial review’ and will draft an alternative wording.  A discussion followed:

- RB asked if the Plan will be reviewed in 2 years

- SB hoped that the Plan’s processes will be embedded into the BTTC calendar

- MI noted that the Plan may need to be reviewed in light of any the forthcoming Local Plan

- RB felt that the Plan would a ‘living’ document and would need to respond to certain changes.  The possible requirements of any further consultation to these potential changes were discussed

- MB stated that the Plan was a standing document and it is not yet clear when a new Plan would be needed to make any necessary changes

- RB felt that the projects should give a clear indication that the Plan’s objectives are being met or not met

- MI stated that Plan can be reviewed to match national planning guidance or Local Plan.  In the absence of this, it should be reviewed every two years (or at agreed period).  MI to draft wording and send to MEd for circulation.

Any small changes to Plan should be sent to MEd for compilation.  The latest version will then be sent to LBP.

RB will be in Italy from 10th July, please call him if you have any queries as his internet connection will be poor.

11) Date of next online meeting: Thursday 30th July 2020 at 7.00pm.

Summary of Actions:

- SB will send MEd the re-drafted Housing document

- MI will send the re-drafted Traffic document to MEd

- MI will send Traffic Section to DCC asap for approval

- RB will liaise with Debbie Fletcher (DF) about timescales for the Environment group

- MW will circulate the Briefing Note on Referendums (for NDPs) (Subsequently circulated on 6 July 2020.)

- SB will check with ML that the Dropbox link is acceptable for appendices etc for statutory consultees

- RB will give MW the changes to the draft press release.  The redraft will be circulated to SG for comment by a deadline

- RB/MW to buy a mobile phone with an answer-phone service

- MEd will ask Cllr Jason Cole (JC) to quote for compilation of appendices

- SB will check whether a number of quotes for a) compilation of appendices and b) front cover design as JC is a BTTC Councillor

- MI to draft wording for Review Section and send to MEd for circulation

- All:

  - Read draft Chair’s Intro and send comments to MEd

  - Any small changes to Plan should be sent to MEd for compilation.