Bovey Parish Neighbourhood Plan

Minutes of the 30th Steering Group ONLINE Meeting

30th July 2020 at 7.00 pm

Attending:

Cllr Ulli Arnold (UA) – (Joined at 8.2)

Mark Bailey (MB)

Cllr Robert Bradshaw (RB) - Chair

Cllr Sheila Brooke (SB) - ex officio

Marion Edwards (MEd)

Martyn Iles (MI)

Cllr Eoghan Kelly (EK) – (Left at 8.2)

Alan Taylor (AT)

Lisa Robillard Webb (LRW) – Minute-taker

- Welcome, Introductions & Apologies: - Apologies: Mark Wells (MW)

- Declaration of Interests: - None declared.

- Climate Emergency: - Statement noted.

- Minutes: -

4.1 - Approval of minutes: 2nd July 2020 minutes agreed by all.

4.2 Review of Actions:

- Completed - SB will send MEd the re-drafted Housing document

- Completed - MI will send the re-drafted Traffic document to MEd

- Completed  (MI will ask MW on 3.8.20 to chase up DCC for a response and to ask if the timetable will be impacted on in the meantime) - MI will send Traffic Section to DCC asap for approval

- Completed (MEd & SB said that Environment issues have been resolved and the necessary changes added to the draft Plan – HRA will be discussed later in the meeting) - RB will liaise with Debbie Fletcher (DF) about timescales for the Environment group

- Completed - MW will circulate the Briefing Note on Referendums (for NDPs) (Subsequently circulated on 6 July 2020.)

- Completed (Link is acceptable and MEd thinks that it works) - SB will check with ML that the Dropbox link is acceptable for appendices etc for statutory consultees

- Completed (MEd had sent comments, SB will ask MW to re-circulate the latest draft to the SG, any comments to be made by close of play 31.7.20, if no comments made, agreement will be implied) - RB will give MW the changes to the draft press release.  The redraft will be circulated to SG for comment by a deadline

- Completed (MI bought one and MEd has the number.  Answerphone can be accessed without the handset. £10 worth of calls included) - RB/MW to buy a mobile phone with an answer-phone service

- Completed (All JC work to be pro-bono) MEd will ask Cllr Jason Cole (JC) to quote for compilation of appendices

- Completed (All JC work to be pro-bono) - SB will check whether a number of quotes for a) compilation of appendices and b) front cover design as JC is a BTTC Councillor

- Completed - MI to draft wording for Review Section and send to MEd for circulation

- Individual completion - All:

  - Read draft Chair’s Intro and send comments to MEd

  - Any small changes to Plan should be sent to MEd for compilation.

- Matters arising not on the agenda:

5.1: To receive matters arising not covered on the agenda: None given. 8.1 now discussed and minuted under the 8.1 section.

- Chair and Vice Chair Reports

6.1: Chair Report:  None given.

6.2: Vice Chair Report: None given.

- Secretary and Treasurer Reports:

7.1: Secretary Report:  None given.

7.2: Treasurer Report (MB):

There has been no income or expenditure since the last SG meeting so the budget figures remain:

Income to date:         £13,278.00

Expenditure to date: £10,239.17

Current balance:          £3,038.83 [split between £294.48 restricted (9.7%) and £2,744.35 unrestricted (90.3%) funds].

RB has spoken to MW about re-deploying some of the restricted funds (MB noted that only £294 was in this fund, as LB Planning took a significant amount.  There may be £2870 available from groundworks).  MB asked the SG if any costs were to be imminently paid.  Money now saved as postage stamps not to be used and plastic roadside banners not to be bought due to environmental concerns.

*Discussion on leaflet delivery took place here but minuted under 8.2.

- Notified Items:

8.1:  Receive and consider the HRA and agree any action as appropriate (RB)

After discussion, SG agreed to take the last three sentences of Michelle Luscombe’s (ML) from TDC e mail on HRA and SEA and add at the bottom of the Chair’s Statement.  This will demonstrate at the start of the document that the SG has endeavoured to comply with the stated requirements.

SB thanked MI for his hard work on the poster and leaflet, especially for keeping to the remit.  Chris Robillard will do the final layout.  The members debated whether to have a short statement on compliance in the leaflet.  MI and MB suggested a slight rewording so that it emphasises that delivery will be made to the residents’ properties.  At MW’s suggestion, a link to the HRA and SEA could be added to the bottom of the Chair’s Statement (to be re-checked with MW and TDC).  But MI noted that TDC will do a screening of the HRA and SEA to see if they are needed and then pass it onto DNP; due to staffing issues a response may be delayed.  ML will give the SG any subsequent comments from the DNP.

8.2 Receive and consider the draft pre-submission consultation leaflet and agree any action as appropriate (MI):

MEd requested that residents are given the opportunity to receive a hard copy of the full draft Plan, page 2 doesn’t indicate how they can access a copy.  SG discussed this situation:

- Residents can phone to request a copy.  Agrees that there is conflicting advice on access to hard copies ie ‘single-use’ copies in the library

- EK encouraged the SG to consider environmental concerns in producing numbers of hard copies

- SB said that we could provide the link and encourage the residents to use the library’s computers if they do not have access to one (however due to the Covid-19 crisis the library’s equipment is not available)

SG agreed to stay with the current format with a link in the leaflet (MEd abstained).  MB is happy to go with the SG in calling the document ‘leaflet’ instead of ‘booklet’.  MI has sent some suggested changes to MEd.  RB will go through final draft tomorrow.

UA joined the meeting as EK left.

Deadlines discussed so that the delivery deadline of 14 August will be kept (Chris Robillard (CR) going away on holiday).  Get the draft to CR asap and it may be possible to make minor changes afterwards.  SB/RB to confirm with MW.

* Detailled discussion from 6.2:

Volunteers needed to deliver leaflet to approximately 500 outlying properties. CR to provide a list of areas not delivered to by his team. The SG could ask other members of the NP group to help.

Long debate held on how to process feedback on the leaflet:

- Standard auto response to e mails coming in with feedback.  But with some flexibility  to respond to some specific requests

- Disclosure of residents’ names when offering feedback:

  - Follow Data Protection and GDPR standards(SB)

  - Chudleigh Consultation document may be useful to refer to – they had four columns: Respondent’s Name, Comment, Response Back, Change to Plan’s Wording (MEd)

  - Collate responses without names and therefore potential bias, especially in such a small town.  Names could be added at a later date, if necessary but not at the initial stage.  Explicitly let respondents know if their names are to be published (SB)

  - TDC can offer advice – they do show names on planning consultations etc (MEd)

  - Tell residents in the Consultation Statement how their comments will be captured (RB)

  - Show postcodes to see any potential patterns (MI).  But not an exact indicator (MB). If a significant number received, an indication can be explored (MI).  Quantitative data as well as qualitative (RB)

  - Names shown in newspaper’s Letters Page.  Responders could stand by their comments if name published(MB)

  - Demonstrate process to the Examiner (RB).

MI, SB ask ML for advice at TDC plus MW at BTTC.  MEd confirmed that everything necessary will be included in the Consultation Statement (proof-readers and Cllr Tony Allen’s comments were noted).

Discussion held on how to aggregate the respondents’ feedback.  MB explained the former two-phase process of guillotining the paper responses into subject groups and giving to the Working Group Leads to collate and analyse.  This is not possible now as feedback will largely be via e mail. (Chudleigh received circa 100 responses).  LRW offered to collate the initial responses into work group categories and on completion, handover to Working Group Leads.  In addition, one full document of responses collated and circulated.  Other NP volunteers could review the results.  RB stated that the SG will need to demonstrate how the comments have changed the draft Plan.

LRW noted that respondents may offer responses that cross a number of the subjects.  Each respondent could be coded with their postcode and an individual number, so that they can be tracked back to a database.

Agreed process:

- E mail responses come into an address monitored by MW and forwarded to LRW for collation

- An agreed auto-response with a message from the Chair sent back to each respondent, to include an approximate date (six months?) for the revised Plan to be available online (MEd)

- Working Group Leads could respond to individual questions that require an answer beyond the generic e mail acknowledgement

- Any callers to the phone will be asked to write down their thoughts and MB will arrange to collect the response from the home address.  Covid-19 hygiene to be observed.

8.3 Receive and consider the draft pre-submission consultation poster and agree any action as appropriate (MI)

RB thought that the design of poster strong.  30 to 40 posters to be printed (to include a mix of A4 and A3 sizes).  No lamination due to environmental concerns.  SB will distribute throughout local notice-boards, facilities and shops.  RB will take some to Heathfield (school, Mole Valley etc).  Residents can display them as well.  AT suggested e mailing as a pdf so people can print it off themselves and display.  SG signed off the content.

- Work group reports:   Not discussed.

- Communications:

10.1 – Correspondence & Information: Not discussed

10.2 – Public Relations & Press Releases:

MEd will e mail Map A to the SG.  She asked if the consultation poster can go the community Facebook page ‘What’s on Bovey’ with the comments section switched off.

- AOB:

11.1 Brief items and/or to the next agenda:

RB thanked UA for his attendance.

MEd let the SG know that the draft Plan will go to JC for layout by Monday 10th August 2020.

SB asked SG members to consider volunteering for the temporary school road closures – RB, MI, MB and MEd indicated interest.

12) Date of next online meeting:

Brief operational meeting for 30 minutes on Monday 10th August 2020

Next NPSG Meeting on Thursday 3rd September 2020 at 7.00pm.

Summary of Actions:

- MI to ask MW on 3.8.20 to chase up DCC for a response on the Traffic Section and to ask if the timetable will be impacted on in the meantime

- SB to ask MW to re-circulate the latest press release draft to the SG, any comments to be made by close of play 31.7.20, if no comments made, agreement will be implied

- RB to oversee agreed changes to the Chair’s Statement  eg inclusion of the last three sentences of Michelle Luscombe’s (ML) from TDC e mail on HRA and SEA etc

- SB/RB to confirm delivery dates and final draft of leaflet time-frame with MW

- MI, SB to ask ML for advice at TDC plus MW at BTTC on disclosure of respondents’ names

- MEd to e mail Map A to the SG

- MW to add consultation poster onto the community Facebook page ‘What’s on Bovey’ with the comments section switched off

- SB to distribute the poster throughout local notice-boards, facilities and shops

- MI to take some posters for display to Heathfield (school, Mole Valley etc).