Bovey Parish Neighbourhood Plan

Minutes of the 22nd Steering Group Meeting

9th January 2020 at 7.00 pm

Attending:

Cllr Ulli Arnold (UA)

Julie Arnold (JA)

Cllr Robert Bradshaw (RB) – Chair

Mark Bailey (MB)

Marion Edwards (MEd)

Martyn Iles (MI)

Cllr Eoghan Kelly (EK)

Alan Taylor (AT)

Lisa Robillard Webb (LRW) – Minute-taker

- Welcome, Introductions & Apologies: - Apologies: Cllr Sheila Brooke (SB) - ex officio

- Declaration of Interests: - None declared.

- Climate Emergency: - Statement unread.

- Minutes: -

4.1 - Approval of minutes: RB asked members to e mail any proposed amendments him.  The 12th December 2019 minutes will be discussed and signed-off at February’s NPSG meeting.

- Chair and Vice Chair Reports:

5.1: None given.

5.2: None given.  RB will clarify with TW about his future involvement in the steering group.  MB noted that the draft minutes explained the current status.  RB will contact TW.

- Secretary and Treasurer Reports:

6.1: Secretary Report:  No report given.  LRW asked for confirmation of NPSG meeting dates to stay as the first Thursday of every month.

6.2: Treasurer Report (MB):

Income to date:       £10,278.00

Expenditure to date: £6,876.92

Current balance:        £3,401.08 [split between £3,285.48 restricted (97%) and £115.60 unrestricted (3%) funds]

The income figure includes two restricted grants totalling £1,148 from the Tracey Almshouse Trust for a Green Space Assessment and photography for the neighbourhood plan document.

- Notified Items:

7.1 Workshop on Saturday 11th January 2020:

Workshop format:

- Use the draft of the Neighbourhood plan circulated by MW at 4.12pm on 16 December 2019

- Peer review document - focusing on the policies and principles (statutory documents can be quickly dealt with)

- 9.00am Coffee, 9.30am Start and Finish at 1.15pm the latest

- MED asked if each working group will have a representative – not sure yet

- 3 members (including RB) will annotate the discussion.  MED has asked MW for three copies of the plan (single sided) to be provided. After the meeting, these notes will be collated into a further draft of the Plan to be then agreed

- RB will pick up the projector and will have the Plan document loaded into his laptop.

- Work group reports:

Housing:  Work still needed to be done, concern over the deadline.  JA/RB to discuss

Land & Environment: No representative at the meeting

Community Facilities:  MEd has produced and circulated document

Traffic: MI – Parking audit completed and the feedback is being used on the policies.  The deadline is fine. RB asked if it could be useful for the Traffic Plan – UA agreed and JA said that it would be helpful for Housing as well

Business & Employment:  EK has requested the documents from SL and is working on the policies/projects.  He will have something to circulate on Saturday.

Further discussion was held on the use of CIL funds and whether the Housing section could qualify for CIL funding.  UA suggested that the Plan’s projects may give suggestion of how potential CIL monies could be spent.  RB will bring along other Neighbourhood Plans to Saturday’s workshop to give a steer on how this subject can be handled in the Plan.

The involvement of Business for Bovey (BFB) was discussed.  It would be good to share a draft of the Plan with them after Saturday’s workshop.  This led to a discussion on key stakeholders.  MEd noted that stakeholders should be listed at the end of the policies for group-wide collation.  MB suggested that TDC would have list of the stakeholders, RB wondered if this included the specific local contacts. MEd said that TDC would look at stakeholders in the scrutiny and pre-referendum analysis.

- Communications:  A group update may be send to the Press after Saturday’s workshop.

- AOB:

Climate Impact:  None.

Plan Programme:  MI asked if there was an up to date programme to be circulated, MEd confirmed that there was.  RB requested that any changes to the programme needed to be sent in.

- Date of next meeting: Thursday 6th February 2020 at 7.00pm

Meeting concluded at 7.42pm.

Summary of Actions (apart from Saturday 11th January’s workshop):

- All members to e mail:

- any proposed amendments to the 12 December 2019 minutes to RB

- any changes for the Plan’s programme

- RB to clarify with TW about his future involvement in the steering group

- JA/RB discuss the Housing Group progress.