Bovey Parish Neighbourhood Plan

Minutes of the 12th Steering Group Meeting

6th December 2018 at 7.00 pm

Attending:

Julie Arnold (JA)

Cllr Ulli Arnold (UA)

Cllr Janet Blair (JB)

Marion Edwards (MED)

Cllr Martyn Evans (ME)

Martin Iles (MI)

Cllr Eoghan Kelly (EK) - Chair

Cllr Steven Leigh (SL)

Amber MacDonald (AM)

Tom Wilson (TW)

Lisa Robillard Webb – Minute-taker

- Apologies: Mark Bailey (MB)

- Declaration of Interests: – None declared

- 3.1 Review of Minutes of the Previous Meeting (11/10/2018) – Minutes agreed.

3.2 Review of Actions:  One update given:

  - Completed - EK to ask Mark Wells if Sibelco have provided a map of the land they own.  The map details underground ownership.

7.)  7.1 Statement

(Item 7 brought forward before Cllr Janet Blair had to leave for another engagement.)

Statement from Marion Edwards, 6th December 2018:

“Colleagues, You may recall that shortly after we started work on the NP, I volunteered to edit the Plan when that time arrived. My expectation of the job was that it comprised three tasks - that I should produce a document with consistent style and layout, amend obvious errors and consult on other issues I encountered.  My first editing job was the posters for the second engagement. The graphic designer had given us Monday 15th October as our deadline for submitting the copy for our posters. The Steering Group meeting to approve the poster wording was on Thursday 11th giving me three days to retype, edit and consult the working group leaders. It turned out that my understanding of the work of an editor was different to some of yours and to my disappointment I was not able to carry out, to my satisfaction, any of the three tasks I mentioned.  No doubt these differences could all have been satisfactorily resolved had the timeframe been longer, giving time for consultation between us. As it was, I spent three days working on this and at the end it seemed I had not done what was expected or required.  You may be surprised to hear that I am now relieved I had that experience as I realise that, given the above, I am not the correct person to edit the full plan. I therefore withdraw my offer to do this (indeed I emailed Eoghan on October 14th and said “I will not be doing that again”) and suggest that alternative arrangements need to be made in the near future, as we are now moving into the “writing up” stage.  I am very happy to continue writing and indeed, along with a number of my community SG colleagues am writing a Consultation Statement as we progress with our consulting activities.  I would like this statement to be minuted verbatim and hereby pass the text to the Secretary.”

- 4.1 Chair Update: None given.

4.2 Vice Chair Update:  TW & MW attended a presentation on the Dartmoor National Park’s (DNP) draft Development Plan; it was reassuring that DNP is facing similar issues.  With regards to Housing Needs Analyses, DNP has different targets as a National Park.  Joanna Rumble is the group’s link person. DNP have verbally agreed that the NPSG can look at and use the draft.  A copy of the presentation is available to the group via MW on request.  EK to check with MW if it can be displayed on the group’s page of website.

- Public Responses to Consultation:

5.1 To discuss and agree any review to the Vision/Objectives (how and when by)?

A written summary of responses from each working group needs to be completed prior to the meeting on 7th February 2019.  Draft work to be circulated to TW by 17th January 2019.  A majority of the respondents were positive to the wording of the draft objectives. A discussion was held by members on the next steps; advice included:

- Only a summary of comments is required

- Use Mark Bailey’s document as a method of sorting comments into categories

- Sort comments into objective or policy categories, if necessary

- Use common sense when considering responses to Consultation Statement comments.

MI mentioned the respondents’ impatience to see a one way system under the Traffic Objectives.  MED had contacted the Doctors’ Surgery about the respondents’ call for a new medical centre.

- Consultation Statement:

6.1 To discuss the requirements, what’s involved and agree action as appropriate (MED):

MED has been using 3 key documents to help – Planning Aids; How to write a Consultation Statement; Approaches to Consultation Statements.  MED will do an initial draft – TW & MB helping; most of the material will go into the appendices.   MED will need facts and figures from each working group.  MI noted that the group may need to consult with external bodies but will become apparent in February – the group will need to coordinate approaches.  MED to verify if there is a statutory list of consultees. TW will provide a 5 criteria list to working groups by 17 January 2019.  For example, for each group of objectives: who are the stakeholders? Who needs to be communicated to? What needs to go in the Consultation Statement?

- See the start of the minutes.

- DCT Policy Planning Workshop:

8.1 To receive a verbal report following the workshop

AM, MED &TW attended.  Notes have been circulated and merit study.  The course covered the general principles of neighbourhood plans.  An independent examiner advised that the plan should be coherent, well written and evidenced.  AM emphasised that the group should manage expectations and be clear what the plan can achieve within a reasonable timeframe.  Use stakeholders to support the delivery of the plan.

8.2 Discuss next steps for Policy Planning:

Group can read other similar neighbourhood plans for the wording of similar objectives. TW to confirm whether David Kiernan, Teignbridge District Council (TDC) would like draft objectives in one document or each working group to send theirs once ready.

- Project Plan:

9.1 To receive updated project plan for next 3-months and agree actions as appropriate (MED):

MED updated and circulated the Project Plan.  An achievable timeline is outlined to support the development of a high quality neighbourhood plan.  EK noted that there are Local Elections in May 2019 which may have an impact on some of the group’s current members.  Thanks were given to MED for the work on the Project Plan.

- Pre-submission:  To be re-submitted for February 2019’s agenda.

- Steering Group Vacancy:

11.1 To discuss the SG Vacancy (TW):  Alan Taylor has been involved in the Transport Working group.  Group agreed to invite Alan along to the February meeting with a view to joining.  MW to send a formal invitation to Alan Taylor.

- Date of Next Meeting:  Thursday 7th February 2019 at 7pm. (Group agreed that there will be no meeting in January 2019 so that the working groups can complete the consultation responses summaries.) SG members to maintain email contact, and monitor progress.

- AOB: Vision – JB, MED & UA to continue as the Vision working group.  Comments from consultation to be sent to MED by 2nd January 2019.

- Summary of Actions:

  - EK to check with MW if the draft DNP development can be displayed on the group’s page of website

  - MED will do an initial draft of Consultation Statement by 7th February 2019’s meeting

  - MED to verify if there is a statutory list of consultees for the Consultation

  - TW will provide a 5 criteria list to working groups by 17 January 2019

  - TW to confirm whether David Kiernan (TDC) would like draft objectives in one document or for each working group to send their objectives once ready

  - MW to add ‘Pre-submission’ to 7 February 2019’s NPSG meeting agenda

  - MW to send a formal invitation to Alan Taylor for 7 February 2019’s NPSG Meeting

  - All working groups to:

    - Send a written summary of consultation responses to TW by 17th January 2019

    - Circulate a copy of the above to the NPSG prior to the meeting on 7th February 2019

    - Give facts and figures to MED, as required for the Consultation Statement

d.    Send comments from consultation on Vision to MED by 2nd January 2019.

BPNP./Minutes&agendas/SG minutes06:12:18.docx